## Iteration 1
Time (hr)
| Task | Sub task | Estimated | Tracked
1.1 | Planning | Estimate time |  | 1.83
1.1 | Planning | Timeboxing |  | 1
1.2 | Risk analysis | Identify risks |  | 1.25
1.2 | Risk analysis | Plan risk counter measures |  | 1.58
1 | Project management |  | 5.66 | 5.66
2.2 | Vision | Create vision document |  | 2
2.3 | Use case-model | Create casual UC’s |  | 2.25
2.3 | Use case-model | Create UCD’s |  | 1.17
2.1 | Review | Review RS work |  | 1
2 | Requirements specification |  | 6.42 | 6.42
3.2 | Use case-model | Flesh out UC model with more detail |  | 0
3.2 | Use case-model | Create formal UC |  | 1.65
3.2 | Use case-model | Create activity diagrams |  | 1.75
3.3 | Supplementary specification | Add supplementary details |  | 1.25
3.4 | Data dictionary | Create data dictionary |  | 1
3.5 | Domain model | Create domain model |  | 1.25
3.1 | Review | Review DRS & OOA work |  | 1
3 | Detailed req specification and OOA |  | 7.9 | 7.9
4.2 | Use case-model | Create SSD |  | 1.25
4.2 | Use case-model | Create OC’s |  | 1.75
4.3 | Domain model | Update domain model |  | 0.25
4.1 | Review | Review detailed OOA work |  | 0.5
4 | Detailed OOA |  | 3.75 | 3.75
5.1 | Static and dynamic design | Create CD | 2 | 1.5
5.1 | Static and dynamic design | Create SD | 2 | 3.5
5.2 | GRASP | Document design w/ GRASP principles | 3 | 3.75
5 | OOD |  | 7 | 8.75
| Total |  | 30.73 | 32.48