## Iteration 1
Time (hr)
| Task | Sub task | Estimated | Tracked
1.1 | Planning | Estimate time | 1 | 1.83
1.1 | Planning | Timeboxing | 1 | 1
1.2 | Risk analysis | Identify risks | 1 | 1.25
1.2 | Risk analysis | Plan risk counter measures | 1 | 1.58
1 | Project management |  | 4 | 5.66
2.2 | Vision | Create vision document | 4
2.3 | Use case-model | Create casual UC’s | 3
2.3 | Use case-model | Create UCD’s | 2
2.1 | Review | Review RS work | 1
2 | Requirements specification |  | 9 | 0
3.2 | Use case-model | Flesh out UC model with more detail | 3
3.2 | Use case-model | Create formal UC | 2
3.2 | Use case-model | Create activity diagrams | 3
3.3 | Supplementary specification | Add supplementary details | 3
3.4 | Data dictionary | Create data dictionary | 5
3.5 | Domain model | Create domain model | 5
3.1 | Review | Review DRS & OOA work | 2
3 | Detailed req specification and OOA |  | 21 | 0
4.2 | Use case-model | Create SSD | 4
4.2 | Use case-model | Create OC’s | 3
4.3 | Domain model | Update domain model | 3
4.1 | Review | Review detailed OOA work | 1
4 | Detailed OOA |  | 10 | 0
5.1 | Static and dynamic design | Create CD | 5
5.1 | Static and dynamic design | Create SD | 4
5.2 | GRASP | Document design w/ GRASP principles | 6
5 | OOD |  | 15 | 0
| Total |  | 59