## Iteration 1
Time (hr)
| Task | Sub task | Estimated | Tracked
1.1 | Planning | Estimate time |  | 1.83
1.1 | Planning | Timeboxing |  | 1
1.2 | Risk analysis | Identify risks |  | 1.25
1.2 | Risk analysis | Plan risk counter measures |  | 1.58
1 | Project management |  | 5.66 | 5.66
2.2 | Vision | Create vision document |  | 2
2.3 | Use case-model | Create casual UC’s |  | 2.25
2.3 | Use case-model | Create UCD’s |  | 1.17
2.1 | Review | Review RS work |  | 1
2 | Requirements specification |  | 6.42 | 6.42
3.2 | Use case-model | Flesh out UC model with more detail | 1
3.2 | Use case-model | Create formal UC | 1
3.2 | Use case-model | Create activity diagrams | 2
3.3 | Supplementary specification | Add supplementary details | 2
3.4 | Data dictionary | Create data dictionary | 3
3.5 | Domain model | Create domain model | 3
3.1 | Review | Review DRS & OOA work | 1
3 | Detailed req specification and OOA |  | 12 | 0
4.2 | Use case-model | Create SSD | 3
4.2 | Use case-model | Create OC’s | 2
4.3 | Domain model | Update domain model | 1
4.1 | Review | Review detailed OOA work | 1
4 | Detailed OOA |  | 6 | 0
5.1 | Static and dynamic design | Create CD | 4
5.1 | Static and dynamic design | Create SD | 3
5.2 | GRASP | Document design w/ GRASP principles | 5
5 | OOD |  | 12 | 0
| Total |  | 42.08 | 12.08